## Team
Initials | Name | Email | GitHub Username
AP | Amisha Patel | Apate203@stevens.edu | https://github.com/patelamisha
MC | Mobitha Chandrasegaram | Mchandr3@stevens.edu | https://github.com/Mobitha
| Github repository | https://github.com/patelamisha/SSW555

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Birth before death | AP | Not started
1 | US02 | Marriage before death | AP | Not started
1 | US03 | Marriage before divorce | MC | Not started
1 | US04 | Divorce before death | MC | Not started
1 | US05 | Multiple births <= 5 | AP | Not Started
1 | US06 | Fewer than 15 siblings | MC | Not Started
1 | US07 | Less then 100 years old | AP | Not Started
1 | US08 | Birth before death of parents | AP | Not Started
1 | US09 | Parent age is greater than 14 | MC | Not Started
2 | US10 | Child marriage | MC
2 | US11 | There are no families with 15 or more siblings | AP
2 | US12 | Husban Sibling | AP
2 | US13 | sibling dad | AP
2 | US14 | child parents too old | MC
2 | US15 | recent birth | AP
2 | US16 | up coming birthday | MC
3 | US17 | child's birth is same date as parents' marriage | MC
3 | US18 | unique families by spouses | MC
3 | US19 | Order siblings by age | AP
3 | US20 | correct gender for role | MC
3 | US21 | male last names | AP
3 | US22 | list living married | MC
3 | US23 | list living single | AP
4 | US24 | list multiple births | MC
4 | US25 | unique families by spouses | AP
4 | US26 | Uncle and aunt | MC
4 | US27 | Corresponding entries | AP
4 | US28 | Include individual ages | MC
4 | US29 | Order siblings by age | AP
4 | US30 | List living single | MC

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
Include Chat didram and fill out below table
Here's a sample burndown chart for a team4:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2021-02-20 | 30
Sprint 1 | 2021-02-20 | 7 | 6 | 120 | 75 | 96
Sprint 2 | 2021-03-06 | 6 | 5 | 220 | 110 | 54.5455
Sprint 3 | 2021-03-20 | 6 | 4 | 310 | 100 | 54
Sprint 4 | 2021-04-03 | 7 | 8 | 430 | 110 | 65.4545
#Team members 2 the sprint * 3 stories per sprint
When we expect to complete all user stories

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2021-02-20 | 25 |  | 0 | 0 | 0

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Source File | Source Function | Source Lines | Test File | Test Function | Test lines
US01 | Birth before death | AP | Not started | 18 | 25
US02 | Marriage before death | AP | Not started | 15 | 30
US03 | Marriage before divorce | MC | Not started | 10 | 20
US04 | Divorce before death | MC | Not started | 12 | 20
US05 | Multiple births <= 5 | AP | Not started | 15 | 25
US06 | Fewer than 15 siblings | MC | Not started | 18 | 20
US07 | Less then 100 years old | MC | Not started | 20 | 20
US08 | Birth before death of parents | AP | Not started | 18 | 16
US09 | Parent age is greater than 14 | MC | Not started | 22 | 32
Review Results
Keep doing:
Accessing docs via google drive
Updating the source code on regular basis
Team gather and comunicate each other via zoom meeting
Avoid:
Desegregate at the last minute
minimalized in person meeting

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Stories
Story ID | Story Name | Story Description
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be greater than current date
US02 | Birth before marriage | Birth date should occur before marriage date of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage date should occur before divorce of spouses
US05 | Marriage before death | Marriage date should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 100 years old | current date should be less than or equal to 100 years birth for all living people.
US08 | marriage date > 18 | List all marrige vs birthdate greater than or equal to 18
US09 | list of living married | List all living married people in a GEDCOM file
US10 | list of deceased | List all people in a GEDCOM file who died in the last 30 days
US11 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US12 | List multiple births | List all multiple births in a GEDCOM file
US13 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US14 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US15 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US16 | Multiple births <= 5 | No more than five siblings should be born at the same time
US17 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US18 | Male last names | All male members of a family should have the same last name
US19 | No marriages to children | Parents should not marry any of their children
US20 | Siblings should not marry | Siblings should not marry one another
US21 | First cousins should not marry | First cousins should not marry one another
US22 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US23 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days
US24 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US25 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US26 | Include partial dates | Accept and use dates without days or without days and months
US27 | List large age differences List all couples who were married when the older spouse was more than twice as old as the younger spouse
US28 | Include individual ages | Include person's current age when listing individuals
US29 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US30 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.